## Drilling Log
BOREHOLE DRILLING LOG
Community | Dr. Timbo's Residence |  | Client | Dr. Timbo
Contractor | WiNGiN Heavy Duty Machines Co. Ltd |  | Borehole Ref. No. | BH-1
Drilling start date | 11th May, 2018 |  | Completion date | 13th May, 2018
Drilling method | Air rotary (DTH hammer) |  | Total depth (m) | 70
District | Western Area Rural |  | BH status | Successful
GPS Coordinate East |  |  | GPS Coordinate North
UTM Zone (28N or 29N) | 28N |  | Elevation (m)
Grouting depth (m) | 20 |  | Drill rig
Depth interval (m) | From time | To time | Penetration rate (m/min) | Sample / lithology description | Drilling diameter (in) | Water strike depth (m)
0-5 | 13:30 | 13:35 | 1 | Reddish brown lateritic topsoil | 6.5
5-10 | 13:36 | 13:41 | 1 | Light yellow clayey laterites | 6.5
10-15 | 13:55 | 14:10 | 0.33 | Light yellow clayey laterites, wet from 12 m | 6.5 | 12
15-20 | 14:14 | 14:26 | 0.42 | Clayey saprolite with weathered granite fragments | 6.5
20-25 | 14:30 | 14:38 | 0.63 | Saprolite, decreasing clay content | 6.5
25-30 | 15:15 | 15:23 | 0.63 | Weathered light colour granite, fractured | 6.5 | 30
30-35 | 15:25 | 15:34 | 0.56 | Light colour granite, slightly weathered, fractured | 6.5
35-40 | 15:38 | 15:48 | 0.5 | Light colour granite, slightly weathered | 6.5
40-45 | 15:50 | 16:01 | 0.45 | Light colour granite | 6.5
45-50 | 16:03 | 16:13 | 0.5 | Light colour granite, fracture zone 49-52 m | 6.5
50-55 | 16:15 | 16:17 |  | Light colour granite | 6.5
55-60 | 16:18 | 16:20 |  | Light colour granite, fracture zone 60-62 m | 6.5
60-65 | 16:27 | 16:31 |  | Light colour granite | 6.5
65-70 | 16:56 | 17:00 |  | Light colour granite, fresh | 6.5
Notes: write depth intervals as 0-5, 5-10 and so on. Enter a water strike depth on the row of the interval where water was struck.